## Sheet1
Sprint | Item backlog | Estimate days | Days remaining | Value
1 | Use case diagram | 3 | 0 | 2
1 | Event table | 1 | 0 | 2
1 | Workflow | 1 | 0 | 1
1 | Use case diagram | 1 | 0 | 1
1 | Use case prioritization | 1 | 0 | 1
1 | Brief use cases | 1 | 0 | 1
1 | Fully dressed use cases | 2 | 0 | 2
1 | Candidate list | 1 | 0 | 3
1 | Mock-ups | 1 | 0 | 1
1 | Domain Model | 3 | 0 | 5
1 | System sequence diagram | 1 | 0 | 2
1 | Interaction diagram | 1 | 0 | 2
1 | Operation contracts diagrams | 1 | 1 | 2
1 | Design class diagram | 21 |  | 5
1 | Relation model | 3 | 3 | 5
1 | Database arhitecture | 3 | 3 | 5