## Sheet2
|  | Sprint |  |  | Time | Time left
ID | Description | #1 | #2 | #3 |  |  | Burndown chart
| Effort needed for release 1 | 126 | 108 | 40
1 | Workflow | 2 | 0 |  | 40 | 39
2 | As is/To be tables | 2 | 0
3 | Use case diagram | 2 | 0
4 | Use case prioritization | 3 | 0
5 | Brief Use Cases | 1 | 0 |  | 39 | 39
6 | Fully dresses use cases | 2 | 0
7 | Candidate class list | 2 | 0
8 | Mock-ups | 4 | 0 |  | 38 | 39
9 | Domain model | 10 | 0 |  | 35 | 30
10 | System sequence diagram Make Order | 5 | 0 |  | 30 | 28
11 | System sequence diagram Create Merchandise | 5 | 0
12 | System sequence diagram Make Reservation | 5 | 0
13 | Interaction diagram Make Order | 6 | 0 |  | 28 | 27
14 | Interaction diagram Create Merchandise | 6 | 0
15 | Interaction diagram Make Reservation | 6 | 0
16 | Design class diagram | 20 | 5 |  | 27 | 23
17 | Relational Model | 20 | 5 |  | 20 | 17
18 | Database architecture | 25 | 5 |  | 17 | 14
Sprint 1 Finish system development requirements
19 | Model layer | 0 | 10 |  | 14 | 15
20 | Database layer | 0 | 20
21 | Exception classes | 0 | 3
22 | Control layer | 0 | 25 |  | 13 | 11
23 | GUI layer | 0 | 30 |  | 11 | 11
24 | Junit tests | 0 | 5 |  | 10 | 9
Sprint 2 Minimal working version
Release 1 Testing version
25 | Implementing check | 0 | 0 | 5 | 9 | 8
26 | Fixing mistakes | 0 | 0 | 5
27 | Implementing new small features | 0 | 0 | 10
Sprint 3 Correcting mistakes and adding new small features
Release2 Final version release
28 | Adding discount | 0 | 0 | 5 | 7 | 5
29 | Adding notifications | 0 | 0 | 15 | 0 | 0
| Effort in the whole backlog | 126 | 108 | 40
| Velocity | 39 | 36 | 34